## Agile Product Roadmap
Agile Product Roadmap: Accessibility Navigator
Phase 1: MVP Development (Months 1-3)
Goal: Launch a functional mobile and web application with core features for locating accessibility ramps.
| Sprint 0 (Weeks 1-2) – Project Setup | Sprint 1 (Weeks 3-4) – User Authentication & Database | Sprint 2 (Weeks 5-6) – Interactive Map & Ramp Details | Sprint 3 (Weeks 7-12) – Testing & Launch
| Set up project structure and hosting. Develop landing page with mission statement. Implement basic navigation (Home, About, Contact). | Implement user registration and login. Create a database for mapping accessibility ramps. Allow users to submit new ramp locations. | Integrate an interactive map with ramp locations. Display ramp details (location, type, accessibility rating). Implement search and filtering options. | Enable user reviews and ratings for ramps. Conduct bug fixes and usability testing. Deploy MVP version of Accessibility Navigator.
Add a reporting system for inaccurate or missing locations.
Create a feedback system for app improvements.
Phase 2: Feature Expansion & User Engagement (Months 4-6)
Goal: Improve user experience and expand features based on feedback.
| Sprint 4 (Weeks 13-14) – Enhanced Map Features | Sprint 5 (Weeks 15-16) – Community Features | Sprint 6 (Weeks 17-20) – Reporting & Transparency | Sprint 7 (Weeks 21-24) – Performance Optimization
| Implement real-time navigation for ramp directions. Add advanced filtering for ramp accessibility levels. | Develop forums for accessibility discussions. Implement a feature for requesting accessibility improvements in specific areas. | Introduce reports on accessibility improvements. Allow users to track contributions and updates on reported ramps. | Improve app speed and scalability. Strengthen security measures for user data protection.
Phase 3: Scaling & Partnerships (Months 7-12)
Goal: Expand the platform’s reach and impact.
| Sprint 8 (Weeks 25-26) – Mobile Optimization | Sprint 9 (Weeks 27-28) – Partnerships | Sprint 10 (Weeks 29-32) – Localization & Marketing
| Improve mobile responsiveness. Ensure compatibility with screen readers and accessibility tools. | Establish partnerships with NGOs, government agencies, and accessibility advocates. Enable organizations to contribute ramp location data. | Expand language support for different regions. Launch campaigns to raise awareness about accessibility issues.

## Project Planning
TEAMS | Engineering Team | UI/UX Team | Content & Strategy Team | Legal & Compliance Team | User Research Team
| Support & Moderation Team | Community & Outreach Team | Finance & Transactions Team | Marketing & Outreach Team | Testing & QA Team
| Research & Project Setup | User Authentication & Database Setup | Interactive Map & Ramp Listings | User Reviews & Reporting System | Real-Time Navigation & Deployment of MVP | Community Forums & Accessibility Directory | Reporting & Contribution Tracking | Performance & Security Enhancements | Mobile Accessibility & Usability Enhancements | NGO & Government Partnerships | Multilingual & Global Expansion
Sprint | Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10
| weeks 1-2 | weeks 3-4 | weeks 5-6 | weeks 7-12 | weeks 13-14 | weeks 15-16 | weeks 17-20 | weeks21-24 | weeks25-26 | weeks27-28 | weeks29-32
1. Project Setup | Set up project structure and hosting. | Implement user registration and login. | Integrate an interactive map with ramp locations. | Enable user reviews and ratings for ramps. | Implement real-time navigation for ramp directions. | Develop forums for accessibility discussions. | Introduce reports on accessibility improvements. | Improve app speed and scalability. | Improve mobile responsiveness. | Establish partnerships with NGOs, government agencies, and accessibility advocates. | Expand language support for different regions.
| Develop landing page with mission statement | Create a database for mapping accessibility ramps. | Display ramp details (location, type, accessibility rating). | Conduct bug fixes and usability testing. | Add advanced filtering for ramp accessibility levels. | Implement a feature for requesting accessibility improvements in specific areas. | Allow users to track contributions and updates on reported ramps. | Strengthen security measures for user data protection. | Ensure compatibility with screen readers and accessibility tools. | Enable organizations to contribute ramp location data. | Ensure accessibility for diverse disabilities.
| Implement basic navigation (Home, About, Contact). |  | Implement search and filtering options. | Add a reporting system for inaccurate or missing locations. | Deploy MVP version of Accessibility Navigator. | Enable users to find local accessibility resources. |  |  |  |  | Launch campaigns to raise awareness about accessibility issues.
Create a feedback system for app improvements.
Optimize app performance for accessibility.
2. Requirement Gathering | Define accessibility standards and user needs. | Allow users to submit new ramp locations. | Test interactive map functionality. |  | Test real-time navigation. | Test community forums and directory functionality. | Test reporting and tracking features. | Conduct performance and security testing. | Test mobile responsiveness. | Test data contribution system. | Test multilingual support.
| Conduct user research and stakeholder engagement. | Gather user feedback on early prototypes.

## Project Scope
Project Scope: Accessibility Navigator
1. Project Overview
Accessibility Navigator is a web and mobile application designed to help Persons with Disabilities (PWDs) locate accessibility ramps and navigate urban areas. The project follows an Agile development approach with a phased rollout of features, usability testing, and community engagement.
2. Project Objectives
Provide a user-friendly interactive map for locating ramps.
Enable user-generated contributions to improve accessibility data.
Implement real-time navigation and community forums for advocacy.
Ensure security, performance, and compliance with accessibility standards.
Foster partnerships with NGOs, government agencies, and accessibility advocates.
3. Sprint-Based Scope of Work
Sprint 0 (Weeks 1-2): Research & Project Setup |  |  | Sprint 1 (Weeks 3-4): User Authentication & Database Setup |  |  | Sprint 2 (Weeks 5-6): Interactive Map & Ramp Listings |  | Sprint 3 (Weeks 7-12): User Reviews & Reporting System
📌 Goal: Define project scope, set up infrastructure, and gather user requirements. |  |  | 📌 Goal: Implement secure user registration and set up the ramp database. |  |  | 📌 Goal: Integrate an interactive map with ramp locations and search functionality. |  | 📌 Goal: Enable user engagement through reviews and reports.
Project Structure & Hosting |  |  | User Registration & Login |  |  | Map Integration |  | User Ratings & Reviews
Set up the development environment, hosting, and version control. |  |  | Create sign-up and login forms with email verification and password recovery. |  |  | Implement Google Maps or OpenStreetMap integration. |  | Implement a star rating and review system for ramps.
Define project architecture, frameworks, and technology stack. |  |  | Implement session management for secure user authentication. |  |  | Display ramp locations with markers, descriptions, and ratings. |  | Allow users to edit or delete their reviews.
User Research & Accessibility Standards |  |  | Database for Accessibility Ramps |  |  | Search & Filtering System |  | Ramp Reporting System
Identify key accessibility challenges for PWDs. |  |  | Set up a secure and scalable database for ramp locations. |  |  | Enable search by location and filtering by ramp accessibility levels. |  | Allow users to report inaccurate or missing ramps.
Define compliance with WCAG 2.1, ADA, GDPR for accessibility and data privacy. |  |  | Define data structure for storing ramps (location, type, accessibility rating). |  |  | Allow users to sort ramps by rating, recency, and type. |  | Categorize reports (e.g., “Blocked Ramp,” “Needs Repair,” “Incorrect Data”).
Conduct stakeholder engagement with accessibility advocates and NGOs. | [5 empty] | User Contributions |  | Testing & Bug Fixes
Landing Page & Navigation Setup | [5 empty] | Allow users to submit new ramp locations with descriptions and images. |  | Conduct usability testing and fix issues with map functionality.
Develop the landing page with mission statement and project introduction.
Implement basic navigation (Home, About, Contact).
Sprint 4 (Weeks 13-14): Real-Time Navigation & Deployment of MVP |  | Sprint 5 (Weeks 15-16): Community Forums & Accessibility Directory |  |  | Sprint 6 (Weeks 17-20): Reporting & Contribution Tracking |  | Sprint 7 (Weeks 21-24): Performance & Security Enhancements
📌 Goal: Implement real-time navigation for ramp routes and launch MVP. |  | 📌 Goal: Introduce discussion forums and a directory of accessibility resources. |  |  | 📌 Goal: Improve user participation and transparency in accessibility improvements. |  | 📌 Goal: Improve app speed, data protection, and scalability.
Navigation System |  | Community Forums |  |  | Accessibility Improvement Reports |  | App Optimization
Provide directions optimized for wheelchair users and PWDs. |  | Enable users to discuss accessibility challenges and share experiences. |  |  | Introduce reports on ramp conditions for authorities and users. |  | Optimize load times for maps and user interactions.
Highlight accessible paths and warn users about obstacles. |  | Allow users to request accessibility improvements in specific locations. |  |  | User Contribution Tracking |  | Reduce server response time for a smoother user experience.
MVP Deployment |  | Accessibility Directory |  |  | Allow users to track reported ramps and their resolution status. |  | Security Strengthening
Deploy the first version of Accessibility Navigator for public testing. |  | Provide a list of local accessibility resources, such as support centers and NGOs. |  |  |  |  | Encrypt user data and prevent security vulnerabilities (SQL Injection, XSS).
Sprint 8 (Weeks 25-26): Mobile Accessibility & Usability Enhancements |  | Sprint 9 (Weeks 27-28): NGO & Government Partnerships |  | Sprint 10 (Weeks 29-32): Multilingual & Global Expansion
📌 Goal: Ensure the app is fully responsive and accessible across devices. |  | 📌 Goal: Establish collaborations to improve ramp data accuracy. |  | 📌 Goal: Support multiple languages and enhance inclusivity.
Mobile Optimization |  | Partner with NGOs & Government Agencies |  | Expand Language Support
Improve layout and interactions for smaller screens. |  | Enable organizations to contribute ramp data. |  | Implement translations for multiple regions.
Test and refine touch controls and gestures. |  | Build a data-sharing system with urban planners and accessibility groups. |  | Ensure Accessibility for Diverse Disabilities
Screen Reader & Assistive Tool Support |  | Awareness Campaigns |  | Improve UI/UX for users with low vision, hearing impairments, and cognitive disabilities.
Ensure compatibility with VoiceOver, TalkBack, and other accessibility tools. |  | Launch social media and outreach programs to promote accessibility.
4. Summary of Deliverables by Sprint
Sprint | Key Deliverables
Sprint 0 | Project setup, research, and hosting.
Sprint 1 | User authentication, database setup.
Sprint 2 | Interactive map, ramp search and filtering.
Sprint 3 | User reviews, rating system, reporting feature.
Sprint 4 | Real-time navigation, MVP deployment.
Sprint 5 | Community forums, accessibility directory.
Sprint 6 | Contribution tracking, accessibility reports.
Sprint 7 | Performance improvements, security enhancements.
Sprint 8 | Mobile responsiveness, assistive tool support.
Sprint 9 | NGO and government partnerships, outreach campaigns.
Sprint 10 | Multilingual support, enhanced accessibility.

## UI&UX
https://www.figma.com/proto/ymVrdxWkjW66U1soD7k0ne/IPT?node-id=2-51&starting-point-node-id=2%3A51

## Teams
Engineering Team |  |  | Community & Outreach Team
Name | Role | Responsibility | Name | Role | Responsibility
Miguel Dela Cruz | Lead Engineer | Oversees technical decisions, ensures project follows best coding practices. | Jessica Fajardo | Community Manager | Engages with users and disability advocacy groups.
Jayson Reyes | Frontend Developer | Develops user interfaces, ensures accessibility compliance. | Clarisse Domingo | Event Coordinator | Organizes online and offline awareness campaigns.
Arvin Bautista | Backend Developer | Manages database, authentication, and API development. | Edwin Castro | Partnership Manager | Builds relationships with organizations and sponsors.
Mark Anthony Navarro | DevOps Engineer | Handles hosting, security, and deployment pipelines.
UI/UX Team |  |  | Finance & Transactions Team
Name | Role | Responsibility | Name | Role | Responsibility
Lara Mae Santos | UI/UX Designer | Designs user-friendly interfaces and accessibility-friendly elements. | Louie Mendoza | Financial Analyst | Manages donation tracking and financial reports.
Bea Francisco | UX Researcher | Conducts usability tests, gathers feedback from PWDs. | Bobby Salazar | Payment Integration Specialist | Ensures secure transactions for donations.
Janine Alcaraz | Graphic Designer | Creates icons, branding elements, and illustrations. | Camille Fernandez | Donor Relations Manager | Communicates with donors and provides transparency reports.
Content & Strategy Team |  |  | Marketing & Outreach Team
Name | Role | Responsibility | Name | Role | Responsibility
Karen Ramirez | Content Strategist | Defines content direction and voice. | Angelica Ramos | Marketing Lead | Plans digital and offline marketing strategies.
Richelle Gonzaga | Copywriter | Writes website content, user instructions, and help guides. | Marvin Uy | Social Media Manager | Manages social platforms and creates engaging content.
Daryl Manalo | SEO Specialist | Ensures website content is optimized for search engines. | Nina Lopez | Advertising Specialist | Runs paid campaigns and sponsorships.
Legal & Compliance Team |  |  | User Research Team
Name | Role | Responsibility | Name | Role | Responsibility
Atty. Ramon Villanueva | Compliance Officer | Ensures legal adherence to accessibility and data protection laws. | Christine Abad | User Researcher | Conducts interviews and usability tests.
Adrian Vergara | Privacy & Security Analyst | Monitors data protection and security measures. | Marco Soriano | Survey Analyst | Gathers and interprets survey data.
Atty. Kristine Mendez | Legal Advisor | Reviews contracts, terms of service, and privacy policies. | Eric Dimaculangan | Behavioral Analyst | Understands how users interact with the platform.
Support & Moderation Team |  |  | Testing & QA Team
Name | Role | Responsibility | Name | Role | Responsibility
Paulo Aquino | Customer Support Specialist | Responds to user queries and technical issues. | John Carlo Velasco | QA Lead | Oversees all testing processes and test case development.
Ma. Teresa Espinoza | Accessibility Consultant | Provides insights on usability for disabled users. | Jasmine Torres | Manual Tester | Conducts hands-on testing for UI, functionality, and accessibility.
Andrew Pascual | Community Moderator | Manages feedback and user discussions. | Kevin Lim | Automation Tester | Develops test scripts for repetitive testing tasks.

## Communication management plan
Sprint 0 | Sprint 0 - Project Setup | Sprint 1 | Sprint 1 - User Authentication & Database | Sprint 2 | Sprint 2 - Interactive Map & Ramp Details | Sprint 3 | Sprint 3 - Testing & Launch | Sprint 4 | Sprint 4 - Enhanced Map Features
Backlog Refinement & Sprint Planning - Day 1 |  | Backlog Refinement & Sprint Planning - Day 1 |  | Backlog Refinement & Sprint Planning - Day 1 |  | Backlog Refinement - Day 1 |  | Backlog Refinement - Day 1
Meeting Type | Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning
Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time
Duration | 1 hour | Duration | 2 hours | Duration | 2 hours | Duration | 2 hours | Duration | 2 hours
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 2 |  | Sprint Planning - Day 2 |  | Sprint Planning - Day 2 |  | Sprint Planning - Day 2 |  | Sprint Planning - Day 2
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type |  | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 3 |  | Sprint Planning - Day 3 |  | Sprint Planning - Day 3 |  | Sprint Planning - Day 3 |  | Sprint Planning - Day 3
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 4 |  | Sprint Planning - Day 4 |  | Sprint Planning - Day 4 |  | Sprint Planning - Day 4 |  | Sprint Planning - Day 4
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 5 |  | Sprint Planning - Day 5 |  | Sprint Planning - Day 5 |  | Sprint Planning - Day 5 |  | Sprint Planning - Day 5
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 6 |  | Sprint Planning - Day 6 |  | Sprint Planning - Day 6 |  | Sprint Planning - Day 6 |  | Sprint Planning - Day 6
Meeting Type | Sprint Check-in | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | One-time | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 45 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 7 |  | Sprint Planning - Day 7 |  | Sprint Planning - Day 7 |  | Sprint Planning - Day 7 |  | Sprint Planning - Day 7
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 8 |  | Sprint Planning - Day 8 |  | Sprint Planning - Day 8 |  | Sprint Planning - Day 8 |  | Sprint Planning - Day 8
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 9 |  | Sprint Planning - Day 9 |  | Sprint Planning - Day 9 |  | Sprint Planning - Day 9 |  | Sprint Planning - Day 9
Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback
Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time
Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 0 |  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4
Sprint Planning - Day 10 |  | Sprint Planning - Day 10 |  | Sprint Planning - Day 10 |  | Sprint Planning - Day 10 |  | Sprint Planning - Day 10
Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective
Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time
Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 | Sprint 5 - Community Features | Sprint 6 | Sprint 6 - Reporting & Transparency | Sprint 7 | Sprint 7 - Performance Optimization | Sprint 8 | Sprint 8 - Mobile Optimization | Sprint 9 | Sprint 9 - Partnerships
Backlog Refinement & Sprint Planning - Day 1 |  | Backlog Refinement & Sprint Planning - Day 1 |  | Backlog Refinement & Sprint Planning - Day 1 |  | Backlog Refinement - Day 1 |  | Backlog Refinement - Day 1
Meeting Type | Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning | Meeting Type | Backlog Refinement & Sprint Planning
Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time
Duration | 1 hour | Duration | 2 hours | Duration | 2 hours | Duration | 2 hours | Duration | 2 hours
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team | Attendees | Engineering Team, Testing & QA Team, Legal & Compliance Team, UI/UX Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 2 |  | Sprint Planning - Day 2 |  | Sprint Planning - Day 2 |  | Sprint Planning - Day 2 |  | Sprint Planning - Day 2
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type |  | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 3 |  | Sprint Planning - Day 3 |  | Sprint Planning - Day 3 |  | Sprint Planning - Day 3 |  | Sprint Planning - Day 3
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 4 |  | Sprint Planning - Day 4 |  | Sprint Planning - Day 4 |  | Sprint Planning - Day 4 |  | Sprint Planning - Day 4
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 5 |  | Sprint Planning - Day 5 |  | Sprint Planning - Day 5 |  | Sprint Planning - Day 5 |  | Sprint Planning - Day 5
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 6 |  | Sprint Planning - Day 6 |  | Sprint Planning - Day 6 |  | Sprint Planning - Day 6 |  | Sprint Planning - Day 6
Meeting Type | Sprint Check-in | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | One-time | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 45 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 7 |  | Sprint Planning - Day 7 |  | Sprint Planning - Day 7 |  | Sprint Planning - Day 7 |  | Sprint Planning - Day 7
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 8 |  | Sprint Planning - Day 8 |  | Sprint Planning - Day 8 |  | Sprint Planning - Day 8 |  | Sprint Planning - Day 8
Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up | Meeting Type | Daily Stand-up
Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily | Frequency | Daily
Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes | Duration | 30 minutes
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 9 |  | Sprint Planning - Day 9 |  | Sprint Planning - Day 9 |  | Sprint Planning - Day 9 |  | Sprint Planning - Day 9
Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback | Meeting Type | Sprint Demo & Feedback
Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time
Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
Sprint Planning - Day 10 |  | Sprint Planning - Day 10 |  | Sprint Planning - Day 10 |  | Sprint Planning - Day 10 |  | Sprint Planning - Day 10
Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective | Meeting Type | Sprint Review & Retrospective
Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time | Frequency | One-time
Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour | Duration | 1 hour
Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams | Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer) | Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist) | Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team | Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10 | Sprint 10 - Localization & Marketing
Backlog Refinement & Sprint Planning - Day 1
Meeting Type | Sprint Planning
Frequency | One-time
Duration | 1 hour
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 2
Meeting Type | Daily Stand-up
Frequency | Daily
Duration | 30 minutes
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 3
Meeting Type | Daily Stand-up
Frequency | Daily
Duration | 30 minutes
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 4
Meeting Type | Daily Stand-up
Frequency | Daily
Duration | 30 minutes
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 5
Meeting Type | Daily Stand-up
Frequency | Daily
Duration | 30 minutes
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 6
Meeting Type | Sprint Check-in
Frequency | One-time
Duration | 45 minutes
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 7
Meeting Type | Daily Stand-up
Frequency | Daily
Duration | 30 minutes
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 8
Meeting Type | Daily Stand-up
Frequency | Daily
Duration | 30 minutes
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 9
Meeting Type | Sprint Demo & Feedback
Frequency | One-time
Duration | 1 hour
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team
Sprint 10
Sprint Planning - Day 10
Meeting Type | Sprint Review & Retrospective
Frequency | One-time
Duration | 1 hour
Location | Microsoft Teams
Chairperson | Miguel Dela Cruz (Lead Engineer)
Minutes by | Karen Ramirez (Content Strategist)
Attendees | Engineering Team, UI/UX Team, Content & Strategy Team, Legal & Compliance Team, User Research Team

## User Requirements and Story
User Requirements | User Stories
Persons with Disabilities (PWDs): | For Persons with Disabilities (PWDs):
Easily locate accessible ramps in their area. | As a wheelchair user, I want to find accessible ramps near me so that I can navigate the city independently.
Get real-time navigation directions to ramps. | Acceptance Criteria:
Provide feedback on ramp accessibility (e.g., ratings, reviews). | The app displays a map with nearby ramp locations.
Report inaccurate or missing ramp locations. | Real-time navigation provides directions to the selected ramp.
Accessibility Advocates and NGOs: | For Accessibility Advocates and NGOs:
Collaborate with the app to contribute ramp data. | As an NGO representative, I want to collaborate with the app to add ramp data so that we can improve urban accessibility.
Use the app to promote awareness and advocate for accessibility improvements. | Acceptance Criteria:
Access reports on accessibility improvements and user contributions. | The app provides a portal for NGOs to submit ramp data.
Data is verified and integrated into the app.
General Public:
Learn about accessibility issues and contribute to the community. | For the General Public:
Use the app to support PWDs by adding or verifying ramp locations. | As a concerned citizen, I want to learn about accessibility issues so that I can support the PWD community.
Acceptance Criteria:
The app provides educational content about accessibility
Users can engage in community forums and discussions.
As a volunteer, I want to verify ramp locations so that the app’s data remains accurate.
Acceptance Criteria:
The app allows users to verify ramp locations through photos and descriptions.
Verified ramps are marked as “verified” in the database.

## Fucntional & Non Functional Req
Functional Requirements | Non-Functional Requirements
User Authentication & Management: | Performance
Users can register, log in. | The app should load within 3 seconds on average.
Secure authentication system for user data protection. | Ensure smooth operation on all devices (web, Android, iOS) and networks.
Forgot Password Feature: Users can reset their password via email. | Optimize app speed and scalability to handle up to 10,000 concurrent users.
Accessibility Ramp Database: | Security
Create and maintain a database of accessibility ramps. | Implement strong data encryption for user data protection.
Allow users to submit new ramp locations. | Ensure compliance with data privacy laws (e.g., GDPR, Data Protection Act).
Display ramp details (location, type, accessibility rating). | Regularly update security measures to prevent vulnerabilities.
Interactive Map: | Accessibility
Integrate an interactive map with ramp locations. | Ensure the app is fully compatible with screen readers and other accessibility tools.
Provide real-time navigation to ramps with estimated travel time.
Usability
Community Features: | Provide an intuitive and user-friendly interface.
Enable users to review and rate ramps. | Conduct usability testing with PWDs to ensure the app meets their needs.
Allow users to report inaccurate or missing ramp locations.
Provide a feedback system for app improvements. | Reliability
Develop forums for users to discuss accessibility topics. | Ensure 99.9% uptime for the app.
Track contributions | Implement robust error handling and recovery mechanisms.
Reporting & Transparency:
Introduce reports on accessibility improvements.
Allow users to track contributions and updates on reported ramps.